## Overview & Team Matrix
🌱 VerdantIQ (EcoSphere) — System Tracking & Management Hub
Comprehensive Project Roadmap, Workflow Stage Checklist, System Bug Tracking & Component Registry
PROJECT METADATA
Project Name: | VerdantIQ (EcoSphere) Sustainability Intelligence Platform
System Lead / Solution Architect: | Grish Narayanan S
Frontend & UI/UX Engineer: | Gangash
Software Developer & Tester: | Girijesh
Integration Support: | Godfrey
Tech Stack: | Spring Boot 3.2, FastAPI, XGBoost, Google OR-Tools MILP, Groq AI, React 18, MongoDB, MinIO S3
System Status: | All 7 Core Phases Completed & Integration Tested ✅
👥 TEAM RESPONSIBILITY MATRIX
Team Member | Role | Core Responsibilities | Assigned Modules & Modules Handled
Grish Narayanan S | Solution Architect & Backend Developer (Project Lead) | Design overall system architecture, develop backend services & REST APIs, manage database schemas (MongoDB), integrate ML/AI components, oversee technical decisions, and lead software development. | Spring Boot Core Backend, MongoDB 2dsphere GIS, FastAPI XGBoost Pipeline, Google OR-Tools MILP Solver, Groq AI LLM Gateway
Gangash | UI/UX Engineer & Frontend Developer | Design the UI/UX, develop frontend pages, implement responsive interfaces, 2D Spatial Canvas, dashboards, charts, form controls, mobile/desktop view modes, and ensure smooth user experience. | React Spatial Canvas, Emerald Oasis Theme, Omnibar Command Center, Desktop/Mobile Views, 12 Workspace Nodes, Data Visualization Components
Girijesh | Software Developer & Tester | Develop assigned application modules, assist in backend/frontend implementation, perform functional testing, integration testing, bug fixing, automated test suite maintenance, and quality assurance. | JUnit 5 REST Test Suite, Pytest ML Test Suite, Node 36-Endpoint Integration Suite, Bug Remediation, Telemetry Monitoring
Godfrey | Integration Support | Support frontend-backend integration, assist with AI/ML integration, help resolve cross-origin & storage issues, contribute to documentation, version control, deployment scripts, and technical support. | MinIO S3 Object Storage, CORS Filters, PowerShell Multi-Service Launcher (run-phase11-system.ps1), PDF Statement Generator, Deployment Specs
📈 SYSTEM HEALTH & EXECUTION METRICS
Metric Category | Target Scope | Completed / Verified | Health Status
Core Development Phases | 7 Phases | 7 Completed (100%) | DONE ✅
System REST & ML Endpoints | 36 Endpoints | 36 Tested & Verified (100%) | DONE ✅
Spatial UI Workspace Nodes | 12 Nodes | 12 Fully Interactive Nodes | DONE ✅
Automated Test Suites | 3 Suites (JUnit, Pytest, Integration) | All Passing Cleanly | DONE ✅
Bug Resolution & Refactoring | 7 System Bugs Logged | 7 Resolved / Closed (100%) | DONE ✅
Production Script Launcher | PowerShell Launch Script | Configured & Tested | DONE ✅

## 🗓️ Gantt Chart & Roadmap
🗓️ VerdantIQ System Development Roadmap & Gantt Schedule
Phase-by-phase timeline, task ownership, duration in days, completion percentage, and 12-week schedule grid
Task ID | Phase / Task Description | Assigned Lead | Start Date | Due Date | Duration (Days) | % Complete | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1.0 | PHASE 1: Client UI/UX & Spatial Engine | Gangash | 2026-06-01 | 2026-06-14 | 14 | 100%
1.1 | - Emerald Oasis Design System & Theme | Gangash | 2026-06-01 | 2026-06-04 | 4 | 100% | bar: W1
1.2 | - React 2D Infinite Spatial Canvas Shell | Gangash | 2026-06-05 | 2026-06-09 | 5 | 100% | bar: W1 to W2
1.3 | - Groq AI Omnibar & 12 Workspace Nodes | Gangash | 2026-06-10 | 2026-06-14 | 5 | 100% | bar: W2
2.0 | PHASE 2: Backend REST Services (Spring Boot 3.2) | Grish Narayanan S | 2026-06-15 | 2026-06-28 | 14 | 100%
2.1 | - JWT Auth Security & User Profile Service | Grish Narayanan S | 2026-06-15 | 2026-06-18 | 4 | 100% | bar: W3
2.2 | - Activity Tracker & MongoDB CRUD Endpoints | Grish Narayanan S | 2026-06-19 | 2026-06-23 | 5 | 100% | bar: W3 to W4
2.3 | - Apache PDFBox Monthly Statement Generator | Grish Narayanan S | 2026-06-24 | 2026-06-28 | 5 | 100% | bar: W4
3.0 | PHASE 3: ML Forecasting & OR-Tools Optimization | Grish Narayanan S | 2026-06-29 | 2026-07-12 | 14 | 100%
3.1 | - FastAPI Pipeline & XGBoost 30-Day Forecast | Grish Narayanan S | 2026-06-29 | 2026-07-03 | 5 | 100% | bar: W5
3.2 | - IsolationForest Spike Anomaly Engine | Girijesh | 2026-07-04 | 2026-07-07 | 4 | 100% | bar: W5 to W6
3.3 | - Google OR-Tools MILP Constraint Solver | Grish Narayanan S | 2026-07-08 | 2026-07-12 | 5 | 100% | bar: W6
4.0 | PHASE 4: Geospatial GIS & Storage Tier | Godfrey | 2026-07-13 | 2026-07-19 | 7 | 100%
4.1 | - MongoDB 2dsphere GeoJSON Geofencing | Grish Narayanan S | 2026-07-13 | 2026-07-16 | 4 | 100% | bar: W7
4.2 | - MinIO S3 Proof Upload & Tesseract OCR Integration | Godfrey | 2026-07-17 | 2026-07-19 | 3 | 100% | bar: W7
5.0 | PHASE 5: Generative AI & Groq LLM Gateway | Grish Narayanan S | 2026-07-20 | 2026-07-23 | 4 | 100%
5.1 | - Grounded System Prompt & Chat Endpoint | Grish Narayanan S | 2026-07-20 | 2026-07-21 | 2 | 100% | bar: W8
5.2 | - Local Grounded Fallback Engine & Guardrails | Godfrey | 2026-07-22 | 2026-07-23 | 2 | 100% | bar: W8
6.0 | PHASE 6: Notifications SSE & System Telemetry | Girijesh | 2026-07-24 | 2026-07-26 | 3 | 100%
6.1 | - Real-time Server-Sent Events (SSE) Stream | Girijesh | 2026-07-24 | 2026-07-25 | 2 | 100% | bar: W9
6.2 | - System Health & Telemetry Metrics Endpoint | Girijesh | 2026-07-25 | 2026-07-26 | 2 | 100% | bar: W9
7.0 | PHASE 7: Automated Verification & Production Release | Girijesh | 2026-07-27 | 2026-07-28 | 2 | 100%
7.1 | - JUnit 5 + Pytest + 36-Endpoint Integration Suite | Girijesh | 2026-07-27 | 2026-07-27 | 1 | 100% | bar: W10
7.2 | - PowerShell Launch Automation (run-phase11-system.ps1) | Godfrey | 2026-07-28 | 2026-07-28 | 1 | 100% | bar: W11 to W12

## 📋 Stage & Workflow Checklist
📋 VerdantIQ Stage & Workflow Execution Checklist
Granular task breakdown across system stages: Design, Dev/Build, AI/ML, Testing & Release
Stage | Sub-Stage / Area | Step / Action Item | Status | Owner | Priority | Comment / Verification Note
PRE-RELEASE | System Design | Define project goals, scope, and technical roadmap | Done | Grish Narayanan S | High | Roadmap approved in Deliverable/Readme.md
PRE-RELEASE | System Design | Establish MongoDB GeoJSON schemas & ER diagrams | Done | Grish Narayanan S | High | Documented in SCHEMA.md with 2dsphere indexes
PRE-RELEASE | System Design | Formulate OR-Tools MILP cost vs CO2 math model | Done | Grish Narayanan S | Critical | Formulated with pywraplp SCIP solver
PRE-RELEASE | UI/UX Design | Design Emerald Oasis design system & palette | Done | Gangash | High | #059669 Mint, #0F766E Teal, #F3F7F5 Sage
DEVELOPMENT | Frontend UI | Develop React 18 2D Spatial Canvas & nodes | Done | Gangash | Critical | Pan, zoom, & SVG glowing data streams active
DEVELOPMENT | Frontend UI | Implement Groq AI Floating Omnibar Command Center | Done | Gangash | High | Natural language intent parser integrated
DEVELOPMENT | Frontend UI | Build 3-Mode View Switcher (Canvas, Desktop, Mobile) | Done | Gangash | High | Seamless responsive view toggle verified
DEVELOPMENT | Frontend UI | Build 12 Interactive Workspace Nodes & Cards | Done | Gangash | High | Dashboard, Tracker, Twin, Optimizer, Admin, etc.
DEVELOPMENT | Backend API | Configure Spring Boot 3.2 + Spring Security JWT | Done | Grish Narayanan S | Critical | Role-based access (USER, INSTITUTION_ADMIN, SYSTEM_ADMIN)
DEVELOPMENT | Backend API | Implement Activity Tracker Service & GeoJSON Logging | Done | Grish Narayanan S | High | /api/v1/tracker endpoints with spatial queries
DEVELOPMENT | Backend API | Build Institutional Leaderboard & Aggregation Pipelines | Done | Grish Narayanan S | High | MongoDB $group and $sum aggregations active
DEVELOPMENT | Backend API | Implement Apache PDFBox Statement Service | Done | Grish Narayanan S | Medium | /api/v1/reports PDF downloads operational
DEVELOPMENT | ML & AI Engine | Develop FastAPI XGBoost 30-Day Resource Forecaster | Done | Grish Narayanan S | Critical | /api/v1/ml/forecasts running on port 8000
DEVELOPMENT | ML & AI Engine | Develop Scikit-learn IsolationForest Anomaly Engine | Done | Girijesh | High | /api/v1/ml/explain spike detection active
DEVELOPMENT | ML & AI Engine | Implement Google OR-Tools MILP Solver Endpoint | Done | Grish Narayanan S | Critical | /api/v1/optimizer/solve handling budgets & targets
DEVELOPMENT | ML & AI Engine | Integrate Groq API Llama-3.3 LLM Assistant Endpoint | Done | Grish Narayanan S | Critical | /api/v1/assistant/chat with grounded context
DEVELOPMENT | ML & AI Engine | Build Local Grounded Fallback Engine for offline LLM | Done | Godfrey | High | Ensures zero service interruption on rate-limit
DEVELOPMENT | GIS & Storage | Configure MinIO / AWS S3 presigned proof storage | Done | Godfrey | High | Bill upload & evidence storage connected
DEVELOPMENT | GIS & Storage | Integrate Tesseract OCR for bill text parsing | Done | Godfrey | Medium | Automated kilowatt-hour & cost extraction
DEVELOPMENT | GIS & Storage | Implement MongoDB $geoWithin Geofence Verification | Done | Grish Narayanan S | High | Campus radius verification active
QUALITY ASSURANCE | Testing & QA | Write JUnit 5 Spring Security & REST Controller tests | Done | Girijesh | High | Auth, User, Tracker, and Report tests passing
QUALITY ASSURANCE | Testing & QA | Write Pytest XGBoost & OR-Tools Solver tests | Done | Girijesh | High | MILP boundary & forecasting tests passing
QUALITY ASSURANCE | Testing & QA | Build Node.js 36-Endpoint Integration Test Suite | Done | Girijesh | Critical | Comprehensive end-to-end integration verified
RELEASE / DEVOPS | Deployment | Create PowerShell Multi-Service System Launcher | Done | Godfrey | High | run-phase11-system.ps1 launches all servers
RELEASE / DEVOPS | Deployment | Prepare Production Deployment Manifest & Configs | Done | Godfrey | High | DEPLOYMENT.md ready for Railway, Render, & Vercel
PRE-RELEASE | Dev/Build | Next.js 15 Build Validation & Error Boundary Guards | Done | Antigravity AI | High | 0 build errors across 127 routes, next.config workspace tracing resolved, error.tsx added

## 🐛 System Bug & Change Log
🐛 VerdantIQ System Bug, Defect & Architectural Change Log
Git commit-level issue tracking, root cause analysis, developer assignment, and resolution history
Bug / Ticket ID | Type | Description & Root Cause | Date Identified | Status | Priority | Assigned Developer | Git Commit / Ref | Impacted Module | Action Taken & Fix | Escalation | Date Resolved
BUG-001 | Defect | OR-Tools MILP Solver failed with INFEASIBLE status when budget constraint was set to 0 | 2026-07-10 | Closed | Critical | Grish Narayanan S | feat(optimizer): commit #a7f3d2 | FastAPI / OR-Tools Engine | Added feasibility pre-check and explicit fallback response returning clean INFEASIBLE explanation payload. | N | 2026-07-11
BUG-002 | Defect | Expired or malformed JWT token triggered 500 Internal Server Error instead of 401 Unauthorized | 2026-06-17 | Closed | Critical | Grish Narayanan S | fix(auth): commit #c891e4 | Spring Boot Auth Filter | Configured JwtAuthenticationEntryPoint in Spring Security filter chain to catch ExpiredJwtException. | N | 2026-06-18
BUG-003 | UI Defect | SVG Canvas pipeline connectors misaligned on high-DPI / 4K display viewports | 2026-06-08 | Closed | High | Gangash | fix(canvas): commit #b451d0 | React Spatial Canvas | Refactored SVG path coordinate calculations using dynamic bounding box getters (getBoundingClientRect). | N | 2026-06-09
BUG-004 | Integration | MinIO S3 presigned URL generation threw bucket not found error during initial proof upload | 2026-07-18 | Closed | High | Godfrey | fix(storage): commit #e129f8 | MinIO S3 Service | Added automatic bucket initialization check (bucketExists / makeBucket) at Spring Boot startup. | N | 2026-07-18
BUG-005 | Refactor | Groq AI LLM external API timeout when user query was submitted during peak network latency | 2026-07-21 | Closed | Critical | Grish Narayanan S | feat(ai): commit #d3389a | Groq AI LLM Gateway | Built Local Grounded Fallback Engine returning heuristic recommendations when Groq API exceeds 3000ms response window. | N | 2026-07-22
BUG-006 | Database | Spatial query $geoWithin failed due to missing 2dsphere index on ActivityLog.location | 2026-07-14 | Closed | High | Grish Narayanan S | fix(db): commit #f9801b | MongoDB Database Tier | Created @GeoSpatialIndexed(type = GeoSpatialIndexType.GEO_2DSPHERE) annotation on ActivityLog entity. | N | 2026-07-14
BUG-007 | Defect | Server-Sent Events (SSE) stream closed automatically after 30 seconds idle state in browser | 2026-07-25 | Closed | Medium | Girijesh | fix(notifications): commit #77c2e3 | Notification SSE Service | Implemented scheduled heartbeat comment ping (:ping) every 15 seconds over SseEmitter channel. | N | 2026-07-26
BUG-008 | Build & Runtime Defect | Next.js workspace root lockfile inference warning, missing client error boundaries, speech recognition init state error | 2026-09-18 | Closed | High | Antigravity AI | fix(client): outputFileTracingRoot, error boundaries & voice context | Next.js 15 Client UI (VerdantIQCLIENT) | Added outputFileTracingRoot in next.config.ts, created app/error.tsx & app/global-error.tsx, fixed speech recognition init error state. | N | 2026-09-18

## 🗂️ System Modules & Registry
🗂️ VerdantIQ Application Modules & Subsystem Registry
Overview of system microservices, frontend nodes, database collections, and technical leads
Module ID | Module Name | Layer / Service Tier | Lead Owner | Tech Stack & Libraries | Deployment / Route | Stage | Priority | Test Coverage | Key Capabilities
MOD-001 | Next.js 15 Client UI & Dashboards | Frontend UI | Gangash | Next.js 15, React 19, TypeScript, Tailwind v4, Three.js | http://localhost:3000 | Production Ready | Critical | 100% | 127 Route Pages, App Router, Client Error Boundaries, Voice Controls, Dark Theme
MOD-002 | Groq AI Omnibar | Frontend UI | Gangash | React Context, Web Speech API | Global Floating Bar | Production Ready | High | 100% | Natural language intent recognition, speech input, node navigation
MOD-003 | Spring Boot Core REST Backend | Backend Core | Grish Narayanan S | Java 21, Spring Boot 3.2, Security | http://localhost:8080 | Production Ready | Critical | 100% | JWT authentication, user profiles, activity CRUD, PDF generation
MOD-004 | FastAPI ML & Solver Engine | ML Service | Grish Narayanan S | Python 3.11, FastAPI, Pydantic v2 | http://localhost:8000 | Production Ready | Critical | 100% | XGBoost forecasts, IsolationForest anomaly, OR-Tools solver
MOD-005 | Google OR-Tools MILP Solver | Optimization | Grish Narayanan S | Google OR-Tools (pywraplp) | POST /api/v1/optimizer/solve | Production Ready | Critical | 100% | Constrained linear programming for budget vs CO2 offset optimization
MOD-006 | Groq AI LLM Gateway Service | Generative AI | Grish Narayanan S | Groq API (Llama-3.3-70b) | POST /api/v1/assistant/chat | Production Ready | Critical | 100% | Grounded conversational decision intelligence with structured JSON output
MOD-007 | MongoDB Geospatial Store | Database Tier | Grish Narayanan S | MongoDB 7.0, 2dsphere index | mongodb://localhost:27017 | Production Ready | Critical | 100% | GeoJSON point & polygon storage with $geoNear geofencing
MOD-008 | MinIO S3 & OCR Proof Storage | Object Storage | Godfrey | MinIO Java SDK, Tesseract OCR | http://localhost:9000 | Production Ready | High | 100% | Presigned bill uploads, proof geotagging, automated text extraction
MOD-009 | Real-Time Notifications SSE | Notifications | Girijesh | Spring SseEmitter, Event Bus | GET /api/v1/notifications/stream | Production Ready | Medium | 100% | In-app notifications stream, heartbeat keep-alive, mark-as-read API
MOD-010 | System Telemetry & Monitoring | Monitoring | Girijesh | Spring Actuator, Custom Metrics | GET /api/v1/admin/telemetry | Production Ready | Medium | 100% | JVM memory, MongoDB ping latency, request throughput monitoring
MOD-011 | PowerShell Launch Automation | DevOps | Godfrey | PowerShell 7.x | run-phase11-system.ps1 | Production Ready | High | 100% | Orchestrates Spring Boot, FastAPI, React UI, and Integration Tests
MOD-012 | Node.js Integration Test Suite | Testing & QA | Girijesh | Node.js, Axios, Assert | test-system-endpoints.js | Production Ready | Critical | 100% | 36-endpoint automated verification covering all system endpoints